## Sheet1
Feasibility Study and Schematic Design/Site Plan Approvals Schedule 2021
Lincoln Eliot at 150 Jackson Rd Property |  | 2021-12-09
Task: |  |  | Meeting Date:
Public Facilities - P&S Committee Meeting |  |  | 2022-01-05
● | Site and Building Concept Options Report
School Committee Meeting |  |  | 2022-01-10
● | Site and Building Concept Options Report
LE School Building Committee Meeting/DPW-Transportation Joint Meeting |  |  | 2022-01-11
● | Site/Building Options Evaluation Review
● | Vote - Site/Building Preferred Option
Design Review Committee (DRC) Meeting |  |  | 2022-01-12
● | Site/Building Preferred Option Report
LE School Building Committee - COMMUNITY MEETING |  |  | TBD
● | Site/Building Preferred Option Report
● | Public Comment
DPW - Transportation Division Meeting |  |  | 2022-02-03
● | Site/Building Preferred Option Report
LE School Building Committee Meeting |  |  | 2022-02-08
● | Schematic Design & Site Plan Development Progress Report
Historic Commission |  |  | 2022-02-10
● | Schematic Design and Project Determination Filing
Design Review Committee (DRC) Meeting |  |  | 2022-02-16
● | Schematic Design & Site Plan Development Progress Report
Development Review Team (DRT) Meeting |  |  | 2022-02-23
● | Professional Team Introduction
● | Review DRT Site Review Process/Criteria
● | Schematic Design & Site Plan Development Progress Report
LE School Building Committee - COMMUNITY MEETING |  |  | TBD
● | Site/Building Preferred Option Report
● | Public Comment
Historic Commission |  |  | 2022-02-24
● | Schematic Design Report and Project Determination
LE School Building Committee Meeting |  |  | 2022-03-08
● | Schematic Design & Site Plan Development Progress Report
Design Review Committee (DRC) Meeting |  |  | 2022-03-16
● | Schematic Design & Site Plan Development Progress Report
Development Review Team (DRT) Meeting |  |  | 2022-03-23
● | Schematic Design Progress Report
● | Site Development Plan & Storm Water Management Report
School Building Committee Meeting |  |  | 2022-04-04
● | Schematic Design & Site Plan Development Progress Report
Public Facilities - P&S Committee Meeting |  |  | 2022-04-06
● | Schematic Design & Site Plan Development Progress Report
LE School Building Committee - COMMUNITY MEETING |  |  | TBD
● | Site/Building Preferred Option Report
● | Public Comment
LE School Building Committee Meeting |  |  | 2022-04-12
● | Schematic Design & Site Plan Development Report
● | Vote - authorize submission of documents to DRC for 5-58 Ordinance Site Plan Approval
Design Review Committee (DRC) Meeting |  |  | 2022-04-13
● | Schematic Design & Site Plan Development Progress Report
Design Review Committee (DRC) Meeting |  |  | 2022-04-27
● | Schematic Design & Site Plan Development Report
● | Consider Schematic Design Approval & 5-59 Ordiance Site Plan Approval
LE-NECP School Building Committee - COMMUNITY MEETING |  |  | 2022-05-10
● | Schematic Design & Site Plan Development Progress Report and 5-58 Ordinance Site Plan
● | Public Comment
Design Review Committee (DRC) and SBC Meeting |  |  | 2022-05-11
● | Schematic Design & Site Plan Development Report
● | Vote - 5-58 Ordinance Site Plan Approval
PUBLIC HEARING DOCKET & PUBLIC NOTICES ISSUED – to City Council Clerk by |  |  |  | 2021-05-16
City Council Meeting - 5-59 Site Plan Review Assignment |  |  |  | 2022-05-20
Public Facilities - P&S Committee Hearing |  |  | 2022-06-08
● | Public Hearing on LE Schematic Design & Site Development Plan (& Vote)
Public Facilities - P&S Committee Meeting |  |  | (if needed) 6/22/2022
● | Vote - 5-58 Ordinance Site Plan Approval
Finance Committee |  |  |  | 6/20 or 6/27/2022
● | Project Scope & Budget Review
City Council/School Committee Meeting |  |  | 2022-07-11
● | Schematic Report Presentation
● | Vote - 5-58 Ordinance Site Plan Approval & Funding